Morgan City Harbor and Terminal District

“Port Dock Expansion and Extension (EAST) – PHASE I”

FY 2018 BUILD PROJECT SCHEDULE

| ID | Task Name | Duration | Start | Finish |
| --- | --- | --- | --- | --- |
|  | Project Timeline | 833 Days | 1/4/19 | 4/16/21 |
| 1 | Initiate Project | 1 day | 1/4/19 | 1/4/19 |
| 2 | Data Collection | 2 mons | 1/5/19 | 2/28/19 |
| 3 | Develop Project Alternatives | 1 mon | 3/1/19 | 3/28/19 |
| 4 | Project Alternatives Drawings | 2 wks | 3/29/19 | 4/11/19 |
| 5 | Schedule Pre-Application Meeting | 1 day | 4/12/19 | 4/12/19 |
| 6 | Preliminary Design | 1 mon | 4/13/19 | 5/10/19 |
| 7 | Submit Permit Application | 335 days | 5/11/19 | 4/11/20 |
|  | State Permit (LaDNR) | 270 days | 5/11/19 | 1/17/20 |
| 8 | -Permit Reviewed and Deemed Complete | 1 mon | 5/11/19 | 6/7/19 |
| 9 | -Advertise Permit | 1 mon | 6/8/19 | 7/5/19 |
| 10 | -Receive Comments from public and agencies | 3 mons | 7/6/19 | 9/27/19 |
| 11 | -Engineer to Respond to Comments | 1 mon | 9/28/19 | 10/25/19 |
| 12 | -Second review | 2 mons | 10/26/19 | 12/20/19 |
| 13 | -Issue Permit | 1 mon | 12/21/19 | 1/17/20 |
|  | Federal Permit (USACE) | 335 days | 5/11/19 | 4/11/20 |
| 14 | -Permit Reviewed and Deemed Complete | 1 mon | 5/11/19 | 6/7/19 |
| 15 | -Advertise Permit | 1 mon | 6/8/19 | 7/5/19 |
| 16 | -Receive Comments from public and agencies | 4 mons | 7/6/19 | 10/25/19 |
| 17 | -Engineer to Respond to Comments | 1 mon | 10/26/19 | 11/22/19 |
| 18 | -Second review | 3 mons | 11/23/19 | 2/14/20 |
| 19 | -Issue Permit | 2 mons | 2/15/20 | 4/11/20 |
| 20 | Final Design | 3 mons | 5/11/19 | 8/2/19 |
| 21 | Bid Project for Construction | 1 mon | 3/12/19 | 4/12/20 |
| 22 | Construction Phase | 12 mons | 4/15/20 | 4/16/21 |

# Text boxes

MORGAN CITY HARBOR AND TERMINAL DISTRICT

7327 Hwy. 182 . P. O. Box 1460 . Morgan City, LA 70381

TELEPHONE (985) 384-0850 . FAX (985) 385-1931

Email:  office@portofmc.com . www.portofmc.com